## Final Scorecard
shofazh.com — Enterprise Audit Final Scorecard (2026-06-28)
Category | Score | Grade | Notes
SEO | 74 | B- | Strong authority; index/title hygiene defects
UX | 69 | C+ | Good IA; product-page friction
UI | 76 | B | Modern 'fire & ice' system; unify with store
Performance | 58 | D+ | Estimated — render-blocking fonts + inline CSS/JS
Accessibility | 55 | D+ | Estimated — contrast, alt, targets, motion
Security | 72 | B- | Estimated — strong WAF; needs headers/hardening
Mobile | 63 | C | Estimated — slow LCP; menu/targets
Content | 80 | B+ | Standout — expert, structured, E-E-A-T
Conversion | 56 | D+ | Weak buy-box; no reviews; biggest upside
Trust | 77 | B | Official dealer; pin trust to CTA
OVERALL | 68 | C+ | Solid foundation, under-optimised

## Critical Issues
Top 10 Critical Issues
# | Issue | Biz Impact | SEO Impact | Revenue Impact | Cost | Time
1 | AggregateRating schema without real reviews | High | High | Med | Low | 0.5d
2 | Indexed trashed/?login= URLs (index bloat) | Med | High | Low | Low | 1d
3 | Duplicated-sitename title bug | Med | High | Med | Low | 0.5d
4 | Mobile CWV failure (fonts+inline CSS/JS) [Est.] | High | High | High | Med | 3-5d
5 | Weak above-fold buy-box / no click-to-call | High | - | High | Med | 3-5d
6 | No visible reviews / social proof | High | Med | High | Med | 5-10d
7 | Inconsistent URL encoding strategy | Med | Med | Low | Med | ongoing
8 | Low contrast + missing alt (A11y) [Est.] | Med | Med | Low | Low | 2-3d
9 | Missing security headers / WP fingerprint [Est.] | Med | Low | Low | Low | 1-2d
10 | Two divergent design worlds (marketing vs store) | Med | Low | Med | High | 90d

## Roadmap
Prioritized Roadmap
Priority | Action | Time | Owner | Window
CRITICAL | Remove/condition AggregateRating | 0.5d | SEO/Dev | 30d
CRITICAL | Fix duplicated-sitename title | 0.5d | SEO | 30d
CRITICAL | noindex/410 trashed & ?login URLs | 1d | Dev/SEO | 30d
CRITICAL | Self-host + subset fonts | 1-2d | Dev | 30d
CRITICAL | Images: alt+dimensions+lazy+WebP | 2-3d | Dev | 30d
CRITICAL | Sticky buy-box + click-to-call/WhatsApp | 3-5d | Dev/Designer | 30d
HIGH | Consolidate inline CSS -> cached stylesheet | 3-4d | Dev | 60d
HIGH | Launch + display genuine reviews | 5-10d | Dev/Content | 60d
HIGH | Security headers + WP hardening | 1-2d | Dev | 60d
HIGH | noindex thin tags + URL strategy/redirects | ongoing | SEO | 60d
HIGH | Accessibility pass (contrast/focus/targets) | 2-3d | Designer/Dev | 60d
HIGH | Enrich Offer schema | 1-2d | SEO/Dev | 60d
MEDIUM | Caching + WebP + CDN | 3-5d | Dev | 90d
MEDIUM | Capacity filters + model search | 5-7d | Dev | 90d
MEDIUM | Checkout streamlining | 3-5d | Dev/CRO | 90d
MEDIUM | Calculator lead capture | 3d | Dev/CRO | 90d
NICE | Unify design system / tokens | - | Designer/Dev | 90d+